## Contract 10664-
Company | 1 | McKinstry Co. LLC
Contract | 10664- | UW 4TH FLR LAB
Customer | 208880 | Johnson Controls Inc
Status | 2 | 2-Soft Close
Point of Contact | 72506 | ERIK PIECZATKOWSKI
Contract Items
| Contract Item | Description | Department | GL Department | Original Amount | Markup | Revenue Type | Project Delivery
| 1 | UW 4TH FLR LAB | 02400 | 0240 | 64655 | 0% | Cost to Cost | SP_M
| 2 | Warranty for UW 4th Floor Lab | 02400 | 0240 | 0 | 0% | Cost to Cost | SP_W
| Total |  |  |  | 64655

## Jobs
Jobs | [7 empty] | Original Project Estimates
Job Number | Job Description | Project Manager | Department | GLDepartment | Status | Start | End | Labor | Material | Equiment | Subcontract | ODC | Total Budget
10664-001 | UW 4TH FLR LAB | ERIK PIECZATKOWSKI | 02400 | 0240 | 1-Open | 2014-04-01 | 2014-10-01 | 44028 | 20618 | 3468 | 39166 | 3868 | 111148
10664-002 | Warranty for UW 4th Floor Lab Remodel | ERIK PIECZATKOWSKI | 02400 | 0240 | 1-Open | 2014-10-01 | 2015-10-01 | 1000 | 0 | 0 | 0 | 0 | 1000
Total | [7 empty] | 45028 | 20618 | 3468 | 39166 | 3868 | 112148

## Job 10664-001
Contract | 10664-
Job Number | 10664-001 |  |  |  | Original | Current | Forecast | Projection
Job Description | UW 4TH FLR LAB |  |  | Labor | 44028 | 44028 | 0 | 0
Project Manager | ERIK PIECZATKOWSKI |  |  | Material | 20618 | 20618 | 0 | 0
Department | 02400 |  |  | Equipment | 3468 | 3468 | 0 | 0
GLDepartment | 0240 |  |  | SubContract | 39166 | 39166 | 0 | 0
Status | 1-Open |  |  | ODC | 3868 | 3868 | 0 | 0
Start | 2014-04-01 |  |  | Total | 111148 | 111148 | 0 | 0
End | 2014-10-01
[9 empty] | Sum of Original |  | Abbreviation | [5 empty] | Sum of Curr |  | Abbreviation | [5 empty] | Sum of Forecast |  | Abbreviation | [5 empty] | Sum of Projected |  | Abbreviation
Description | Abbreviation | PhasePrefix | Phase | PhaseDesc | Original | Curr | Forecast | Projected | Phase | PhaseDesc | L | M | E | O | S | Grand Total | Phase | PhaseDesc | L | M | E | O | S | Grand Total | Phase | PhaseDesc | L | M | E | O | S | Grand Total | Phase | PhaseDesc | L | M | E | O | S | Grand Total
Labor | L | 0100 | 0100-0000- - | GENERAL REQUIREMENTS* | 0 | 0 | 0 | 0 | 0100-0000- - | GENERAL REQUIREMENTS* | 0 |  |  | 0 | 0 | 0 | 0100-0000- - | GENERAL REQUIREMENTS* | 0 |  |  | 0 | 0 | 0 | 0100-0000- - | GENERAL REQUIREMENTS* | 0 |  |  | 0 | 0 | 0 | 0100-0000- - | GENERAL REQUIREMENTS* | 0 |  |  | 0 | 0 | 0
Labor | L | 0100 | 0100-0191- - | Travel Time* - Carpenters & Drywall | 0 | 0 | 0 | 0 | 0100-0191- - | Travel Time* - Carpenters & Drywall | 0 |  |  | 0 |  | 0 | 0100-0191- - | Travel Time* - Carpenters & Drywall | 0 |  |  | 0 |  | 0 | 0100-0191- - | Travel Time* - Carpenters & Drywall | 0 |  |  | 0 |  | 0 | 0100-0191- - | Travel Time* - Carpenters & Drywall | 0 |  |  | 0 |  | 0
Labor | L | 0100 | 0100-0192- - | Travel Time* - Electrical | 0 | 0 | 0 | 0 | 0100-0192- - | Travel Time* - Electrical | 0 |  |  | 0 |  | 0 | 0100-0192- - | Travel Time* - Electrical | 0 |  |  | 0 |  | 0 | 0100-0192- - | Travel Time* - Electrical | 0 |  |  | 0 |  | 0 | 0100-0192- - | Travel Time* - Electrical | 0 |  |  | 0 |  | 0
Labor | L | 0100 | 0100-0193- - | Travel Time* - Laborers | 0 | 0 | 0 | 0 | 0100-0193- - | Travel Time* - Laborers | 0 |  |  | 0 |  | 0 | 0100-0193- - | Travel Time* - Laborers | 0 |  |  | 0 |  | 0 | 0100-0193- - | Travel Time* - Laborers | 0 |  |  | 0 |  | 0 | 0100-0193- - | Travel Time* - Laborers | 0 |  |  | 0 |  | 0
Labor | L | 0100 | 0100-0194- - | Travel Time* - Painters | 0 | 0 | 0 | 0 | 0100-0194- - | Travel Time* - Painters | 0 |  |  | 0 |  | 0 | 0100-0194- - | Travel Time* - Painters | 0 |  |  | 0 |  | 0 | 0100-0194- - | Travel Time* - Painters | 0 |  |  | 0 |  | 0 | 0100-0194- - | Travel Time* - Painters | 0 |  |  | 0 |  | 0
Labor | L | 0100 | 0100-0195- - | Travel Time* - Plumbing | 0 | 0 | 0 | 0 | 0100-0195- - | Travel Time* - Plumbing | 0 |  |  | 0 |  | 0 | 0100-0195- - | Travel Time* - Plumbing | 0 |  |  | 0 |  | 0 | 0100-0195- - | Travel Time* - Plumbing | 0 |  |  | 0 |  | 0 | 0100-0195- - | Travel Time* - Plumbing | 0 |  |  | 0 |  | 0
Labor | L | 0100 | 0100-0196- - | Travel Time* - Sheet Metal | 0 | 0 | 0 | 0 | 0100-0196- - | Travel Time* - Sheet Metal | 0 |  |  | 0 |  | 0 | 0100-0196- - | Travel Time* - Sheet Metal | 0 |  |  | 0 |  | 0 | 0100-0196- - | Travel Time* - Sheet Metal | 0 |  |  | 0 |  | 0 | 0100-0196- - | Travel Time* - Sheet Metal | 0 |  |  | 0 |  | 0
Labor | L | 0100 | 0100-0197- - | Travel Time* - Sprinklers | 0 | 0 | 0 | 0 | 0100-0197- - | Travel Time* - Sprinklers | 0 |  |  | 0 |  | 0 | 0100-0197- - | Travel Time* - Sprinklers | 0 |  |  | 0 |  | 0 | 0100-0197- - | Travel Time* - Sprinklers | 0 |  |  | 0 |  | 0 | 0100-0197- - | Travel Time* - Sprinklers | 0 |  |  | 0 |  | 0
Labor | L | 0100 | 0100-0800- - | OTHER DIRECT COSTS | 0 | 0 | 0 | 0 | 0100-0800- - | OTHER DIRECT COSTS | 0 |  |  | 2518 | 0 | 2518 | 0100-0800- - | OTHER DIRECT COSTS | 0 |  |  | 2518 | 0 | 2518 | 0100-0800- - | OTHER DIRECT COSTS | 0 |  |  | 0 | 0 | 0 | 0100-0800- - | OTHER DIRECT COSTS | 0 |  |  | 0 | 0 | 0
Labor | L | 0131 | 0131-0000- - | COORD/PROJ MGMT | 5000 | 5000 | 0 | 0 | 0131-0000- - | COORD/PROJ MGMT | 5000 |  |  |  |  | 5000 | 0131-0000- - | COORD/PROJ MGMT | 5000 |  |  |  |  | 5000 | 0131-0000- - | COORD/PROJ MGMT | 0 |  |  |  |  | 0 | 0131-0000- - | COORD/PROJ MGMT | 0 |  |  |  |  | 0
Labor | L | 0131 | 0131-1050- - | SITE SUPERV / SAFETY | 300 | 300 | 0 | 0 | 0131-1050- - | SITE SUPERV / SAFETY | 300 |  |  |  |  | 300 | 0131-1050- - | SITE SUPERV / SAFETY | 300 |  |  |  |  | 300 | 0131-1050- - | SITE SUPERV / SAFETY | 0 |  |  |  |  | 0 | 0131-1050- - | SITE SUPERV / SAFETY | 0 |  |  |  |  | 0
Labor | L | 0131 | 0131-1150- - | General Construction | 10450 | 10450 | 0 | 0 | 0131-1150- - | General Construction | 10450 | 5000 |  |  |  | 15450 | 0131-1150- - | General Construction | 10450 | 5000 |  |  |  | 15450 | 0131-1150- - | General Construction | 0 | 0 |  |  |  | 0 | 0131-1150- - | General Construction | 0 | 0 |  |  |  | 0
Labor | L | 0131 | 0131-1200- - | CONTRACT SUPPORT | 0 | 0 | 0 | 0 | 0131-1200- - | CONTRACT SUPPORT | 0 |  |  |  |  | 0 | 0131-1200- - | CONTRACT SUPPORT | 0 |  |  |  |  | 0 | 0131-1200- - | CONTRACT SUPPORT | 0 |  |  |  |  | 0 | 0131-1200- - | CONTRACT SUPPORT | 0 |  |  |  |  | 0
Labor | L | 0131 | 0131-1210- - | PURCHASING | 0 | 0 | 0 | 0 | 0131-1210- - | PURCHASING | 0 |  |  |  |  | 0 | 0131-1210- - | PURCHASING | 0 |  |  |  |  | 0 | 0131-1210- - | PURCHASING | 0 |  |  |  |  | 0 | 0131-1210- - | PURCHASING | 0 |  |  |  |  | 0
Labor | L | 0131 | 0131-1300- - | MH - MH - DELIVERIES | 0 | 0 | 0 | 0 | 0131-1300- - | MH - MH - DELIVERIES | 0 |  |  |  |  | 0 | 0131-1300- - | MH - MH - DELIVERIES | 0 |  |  |  |  | 0 | 0131-1300- - | MH - MH - DELIVERIES | 0 |  |  |  |  | 0 | 0131-1300- - | MH - MH - DELIVERIES | 0 |  |  |  |  | 0
Labor | L | 0131 | 0131-1430- - | ESTIMATING | 400 | 400 | 0 | 0 | 0131-1430- - | ESTIMATING | 400 |  |  |  |  | 400 | 0131-1430- - | ESTIMATING | 400 |  |  |  |  | 400 | 0131-1430- - | ESTIMATING | 0 |  |  |  |  | 0 | 0131-1430- - | ESTIMATING | 0 |  |  |  |  | 0
Labor | L | 0131 | 0131-1530- - | MECHANICAL DESIGN | 0 | 0 | 0 | 0 | 0131-1530- - | MECHANICAL DESIGN | 0 |  |  |  |  | 0 | 0131-1530- - | MECHANICAL DESIGN | 0 |  |  |  |  | 0 | 0131-1530- - | MECHANICAL DESIGN | 0 |  |  |  |  | 0 | 0131-1530- - | MECHANICAL DESIGN | 0 |  |  |  |  | 0
Labor | L | 0131 | 0131-1550- - | ELECTRICAL DESIGN | 0 | 0 | 0 | 0 | 0131-1550- - | ELECTRICAL DESIGN | 0 |  |  |  |  | 0 | 0131-1550- - | ELECTRICAL DESIGN | 0 |  |  |  |  | 0 | 0131-1550- - | ELECTRICAL DESIGN | 0 |  |  |  |  | 0 | 0131-1550- - | ELECTRICAL DESIGN | 0 |  |  |  |  | 0
Labor | L | 0131 | 0131-1605- - | MECHANICAL CAD | 800 | 800 | 0 | 0 | 0131-1605- - | MECHANICAL CAD | 800 |  |  |  |  | 800 | 0131-1605- - | MECHANICAL CAD | 800 |  |  |  |  | 800 | 0131-1605- - | MECHANICAL CAD | 0 |  |  |  |  | 0 | 0131-1605- - | MECHANICAL CAD | 0 |  |  |  |  | 0
Labor | L | 0131 | 0131-1615- - | ELECTRICAL CAD | 0 | 0 | 0 | 0 | 0131-1615- - | ELECTRICAL CAD | 0 |  |  |  |  | 0 | 0131-1615- - | ELECTRICAL CAD | 0 |  |  |  |  | 0 | 0131-1615- - | ELECTRICAL CAD | 0 |  |  |  |  | 0 | 0131-1615- - | ELECTRICAL CAD | 0 |  |  |  |  | 0
Labor | L | 0131 | 0131-1630- - | Plumbing Detailing | 0 | 0 | 0 | 0 | 0131-1630- - | Plumbing Detailing | 0 |  |  |  |  | 0 | 0131-1630- - | Plumbing Detailing | 0 |  |  |  |  | 0 | 0131-1630- - | Plumbing Detailing | 0 |  |  |  |  | 0 | 0131-1630- - | Plumbing Detailing | 0 |  |  |  |  | 0
Labor | L | 0131 | 0131-1631- - | Design Assist | 0 | 0 | 0 | 0 | 0131-1631- - | Design Assist | 0 |  |  |  |  | 0 | 0131-1631- - | Design Assist | 0 |  |  |  |  | 0 | 0131-1631- - | Design Assist | 0 |  |  |  |  | 0 | 0131-1631- - | Design Assist | 0 |  |  |  |  | 0
Labor | L | 0131 | 0131-1632- - | CAD Backgrounds | 0 | 0 | 0 | 0 | 0131-1632- - | CAD Backgrounds | 0 |  |  |  |  | 0 | 0131-1632- - | CAD Backgrounds | 0 |  |  |  |  | 0 | 0131-1632- - | CAD Backgrounds | 0 |  |  |  |  | 0 | 0131-1632- - | CAD Backgrounds | 0 |  |  |  |  | 0
Labor | L | 0131 | 0131-1640- - | Piping Detailing | 0 | 0 | 0 | 0 | 0131-1640- - | Piping Detailing | 0 |  |  |  |  | 0 | 0131-1640- - | Piping Detailing | 0 |  |  |  |  | 0 | 0131-1640- - | Piping Detailing | 0 |  |  |  |  | 0 | 0131-1640- - | Piping Detailing | 0 |  |  |  |  | 0
Labor | L | 0131 | 0131-1641- - | Design Assist | 0 | 0 | 0 | 0 | 0131-1641- - | Design Assist | 0 |  |  |  |  | 0 | 0131-1641- - | Design Assist | 0 |  |  |  |  | 0 | 0131-1641- - | Design Assist | 0 |  |  |  |  | 0 | 0131-1641- - | Design Assist | 0 |  |  |  |  | 0
Labor | L | 0131 | 0131-1650- - | MULTIPLE | 0 | 0 | 0 | 0 | 0131-1650- - | MULTIPLE | 0 |  |  |  |  | 0 | 0131-1650- - | MULTIPLE | 0 |  |  |  |  | 0 | 0131-1650- - | MULTIPLE | 0 |  |  |  |  | 0 | 0131-1650- - | MULTIPLE | 0 |  |  |  |  | 0
Labor | L | 0131 | 0131-1651- - | S/M Design Assist | 0 | 0 | 0 | 0 | 0131-1651- - | S/M Design Assist | 0 |  |  |  |  | 0 | 0131-1651- - | S/M Design Assist | 0 |  |  |  |  | 0 | 0131-1651- - | S/M Design Assist | 0 |  |  |  |  | 0 | 0131-1651- - | S/M Design Assist | 0 |  |  |  |  | 0
Labor | L | 0131 | 0131-1652- - | Ticketing / Ordering | 0 | 0 | 0 | 0 | 0131-1652- - | Ticketing / Ordering | 0 |  |  |  |  | 0 | 0131-1652- - | Ticketing / Ordering | 0 |  |  |  |  | 0 | 0131-1652- - | Ticketing / Ordering | 0 |  |  |  |  | 0 | 0131-1652- - | Ticketing / Ordering | 0 |  |  |  |  | 0
Labor | L | 0131 | 0131-1653- - | CAD Backgrounds | 0 | 0 | 0 | 0 | 0131-1653- - | CAD Backgrounds | 0 |  |  |  |  | 0 | 0131-1653- - | CAD Backgrounds | 0 |  |  |  |  | 0 | 0131-1653- - | CAD Backgrounds | 0 |  |  |  |  | 0 | 0131-1653- - | CAD Backgrounds | 0 |  |  |  |  | 0
Labor | L | 0131 | 0131-1900- - | MULTIPLE | 0 | 0 | 0 | 0 | 0131-1900- - | MULTIPLE | 0 |  |  |  | 0 | 0 | 0131-1900- - | MULTIPLE | 0 |  |  |  | 0 | 0 | 0131-1900- - | MULTIPLE | 0 |  |  |  | 0 | 0 | 0131-1900- - | MULTIPLE | 0 |  |  |  | 0 | 0
Labor | L | 0191 | 0191-1000- - | Commissioning Union | 0 | 0 | 0 | 0 | 0191-1000- - | Commissioning Union | 0 |  |  |  |  | 0 | 0191-1000- - | Commissioning Union | 0 |  |  |  |  | 0 | 0191-1000- - | Commissioning Union | 0 |  |  |  |  | 0 | 0191-1000- - | Commissioning Union | 0 |  |  |  |  | 0
Labor | L | 0191 | 0191-1010- - | COMMISSIONING | 0 | 0 | 0 | 0 | 0191-1010- - | COMMISSIONING | 0 |  |  |  |  | 0 | 0191-1010- - | COMMISSIONING | 0 |  |  |  |  | 0 | 0191-1010- - | COMMISSIONING | 0 |  |  |  |  | 0 | 0191-1010- - | COMMISSIONING | 0 |  |  |  |  | 0
Labor | L | 0191 | 0191-1030- - | BALANCING | 0 | 0 | 0 | 0 | 0191-1030- - | BALANCING | 0 |  |  |  |  | 0 | 0191-1030- - | BALANCING | 0 |  |  |  |  | 0 | 0191-1030- - | BALANCING | 0 |  |  |  |  | 0 | 0191-1030- - | BALANCING | 0 |  |  |  |  | 0
Labor | L | 0191 | 0191-1040- - | Start Up | 0 | 0 | 0 | 0 | 0191-1040- - | Start Up | 0 |  |  |  |  | 0 | 0191-1040- - | Start Up | 0 |  |  |  |  | 0 | 0191-1040- - | Start Up | 0 |  |  |  |  | 0 | 0191-1040- - | Start Up | 0 |  |  |  |  | 0
Labor | L | 0600 | 0600-1000- - | WOOD, PLASTICS & COMPOSITES | 0 | 0 | 0 | 0 | 0600-1000- - | WOOD, PLASTICS & COMPOSITES | 0 |  |  |  |  | 0 | 0600-1000- - | WOOD, PLASTICS & COMPOSITES | 0 |  |  |  |  | 0 | 0600-1000- - | WOOD, PLASTICS & COMPOSITES | 0 |  |  |  |  | 0 | 0600-1000- - | WOOD, PLASTICS & COMPOSITES | 0 |  |  |  |  | 0
Labor | L | 2100 | 2100-0000- - | MULTIPLE | 0 | 0 | 0 | 0 | 2100-0000- - | MULTIPLE | 0 | 0 |  |  | 0 | 0 | 2100-0000- - | MULTIPLE | 0 | 0 |  |  | 0 | 0 | 2100-0000- - | MULTIPLE | 0 | 0 |  |  | 0 | 0 | 2100-0000- - | MULTIPLE | 0 | 0 |  |  | 0 | 0
Labor | L | 2100 | 2100-2050- - | FIRE PROTECTION PIPE | 0 | 0 | 0 | 0 | 2100-2050- - | FIRE PROTECTION PIPE | 0 |  |  |  |  | 0 | 2100-2050- - | FIRE PROTECTION PIPE | 0 |  |  |  |  | 0 | 2100-2050- - | FIRE PROTECTION PIPE | 0 |  |  |  |  | 0 | 2100-2050- - | FIRE PROTECTION PIPE | 0 |  |  |  |  | 0
Labor | L | 2200 | 2200-0000- - | Plumbing | 13296 | 13296 | 0 | 0 | 2200-0000- - | Plumbing | 13296 | 12050 |  |  | 0 | 25346 | 2200-0000- - | Plumbing | 13296 | 12050 |  |  | 0 | 25346 | 2200-0000- - | Plumbing | 0 | 0 |  |  | 0 | 0 | 2200-0000- - | Plumbing | 0 | 0 |  |  | 0 | 0
Labor | L | 2200 | 2200-0002- - | SUPERVISION | 0 | 0 | 0 | 0 | 2200-0002- - | SUPERVISION | 0 |  |  |  |  | 0 | 2200-0002- - | SUPERVISION | 0 |  |  |  |  | 0 | 2200-0002- - | SUPERVISION | 0 |  |  |  |  | 0 | 2200-0002- - | SUPERVISION | 0 |  |  |  |  | 0
Labor | L | 2300 | 2300-0000- - | HEATING, VENTILATING, AND AIR CONDITIONING (HVAC)* | 0 | 0 | 0 | 0 | 2300-0000- - | HEATING, VENTILATING, AND AIR CONDITIONING (HVAC)* | 0 | 0 |  |  | 0 | 0 | 2300-0000- - | HEATING, VENTILATING, AND AIR CONDITIONING (HVAC)* | 0 | 0 |  |  | 0 | 0 | 2300-0000- - | HEATING, VENTILATING, AND AIR CONDITIONING (HVAC)* | 0 | 0 |  |  | 0 | 0 | 2300-0000- - | HEATING, VENTILATING, AND AIR CONDITIONING (HVAC)* | 0 | 0 |  |  | 0 | 0
Labor | L | 2320 | 2320-0000- - | MULTIPLE | 0 | 0 | 0 | 0 | 2320-0000- - | MULTIPLE | 0 | 0 |  |  | 0 | 0 | 2320-0000- - | MULTIPLE | 0 | 0 |  |  | 0 | 0 | 2320-0000- - | MULTIPLE | 0 | 0 |  |  | 0 | 0 | 2320-0000- - | MULTIPLE | 0 | 0 |  |  | 0 | 0
Labor | L | 2320 | 2320-0002- - | SUPERVISION | 0 | 0 | 0 | 0 | 2320-0002- - | SUPERVISION | 0 |  |  |  |  | 0 | 2320-0002- - | SUPERVISION | 0 |  |  |  |  | 0 | 2320-0002- - | SUPERVISION | 0 |  |  |  |  | 0 | 2320-0002- - | SUPERVISION | 0 |  |  |  |  | 0
Labor | L | 2330 | 2330-0000- - | Sheet Metal (field) | 3304 | 3304 | 0 | 0 | 2330-0000- - | Sheet Metal (field) | 3304 | 300 |  |  | 0 | 3604 | 2330-0000- - | Sheet Metal (field) | 3304 | 300 |  |  | 0 | 3604 | 2330-0000- - | Sheet Metal (field) | 0 | 0 |  |  | 0 | 0 | 2330-0000- - | Sheet Metal (field) | 0 | 0 |  |  | 0 | 0
Labor | L | 2600 | 2600-0000- - | Electrical Material | 0 | 0 | 0 | 0 | 2600-0000- - | Electrical Material | 0 | 968 |  | 0 | 0 | 968 | 2600-0000- - | Electrical Material | 0 | 968 |  | 0 | 0 | 968 | 2600-0000- - | Electrical Material | 0 | 0 |  | 0 | 0 | 0 | 2600-0000- - | Electrical Material | 0 | 0 |  | 0 | 0 | 0
Labor | L | 2600 | 2600-0100- - | ELECTRICAL - SUPV. | 0 | 0 | 0 | 0 | 2600-0100- - | ELECTRICAL - SUPV. | 0 |  |  |  |  | 0 | 2600-0100- - | ELECTRICAL - SUPV. | 0 |  |  |  |  | 0 | 2600-0100- - | ELECTRICAL - SUPV. | 0 |  |  |  |  | 0 | 2600-0100- - | ELECTRICAL - SUPV. | 0 |  |  |  |  | 0
Labor | L | 2700 | 2700-0000- - | COMMUNICATION SYSTEMS* | 0 | 0 | 0 | 0 | 2700-0000- - | COMMUNICATION SYSTEMS* | 0 | 0 |  | 0 | 0 | 0 | 2700-0000- - | COMMUNICATION SYSTEMS* | 0 | 0 |  | 0 | 0 | 0 | 2700-0000- - | COMMUNICATION SYSTEMS* | 0 | 0 |  | 0 | 0 | 0 | 2700-0000- - | COMMUNICATION SYSTEMS* | 0 | 0 |  | 0 | 0 | 0
Labor | L | 7000 | 7000-0002-000114- | PURCHASING | 0 | 0 | 0 | 0 | 7000-0002-000114- | PURCHASING | 0 |  |  |  |  | 0 | 7000-0002-000114- | PURCHASING | 0 |  |  |  |  | 0 | 7000-0002-000114- | PURCHASING | 0 |  |  |  |  | 0 | 7000-0002-000114- | PURCHASING | 0 |  |  |  |  | 0
Labor | L | 7000 | 7000-0002-000116- | HANDLE & LOAD NONS/M | 0 | 0 | 0 | 0 | 7000-0002-000116- | HANDLE & LOAD NONS/M | 0 |  |  |  |  | 0 | 7000-0002-000116- | HANDLE & LOAD NONS/M | 0 |  |  |  |  | 0 | 7000-0002-000116- | HANDLE & LOAD NONS/M | 0 |  |  |  |  | 0 | 7000-0002-000116- | HANDLE & LOAD NONS/M | 0 |  |  |  |  | 0
Labor | L | 9000 | 9000-0000- - | LOGISTICS - NONUNION | 0 | 0 | 0 | 0 | 9000-0000- - | LOGISTICS - NONUNION | 0 | 0 |  |  |  | 0 | 9000-0000- - | LOGISTICS - NONUNION | 0 | 0 |  |  |  | 0 | 9000-0000- - | LOGISTICS - NONUNION | 0 | 0 |  |  |  | 0 | 9000-0000- - | LOGISTICS - NONUNION | 0 | 0 |  |  |  | 0
Labor | L | 9000 | 9000-1000- - | DISPATCH FOR ALL TRD | 0 | 0 | 0 | 0 | 9000-1000- - | DISPATCH FOR ALL TRD | 0 |  |  |  |  | 0 | 9000-1000- - | DISPATCH FOR ALL TRD | 0 |  |  |  |  | 0 | 9000-1000- - | DISPATCH FOR ALL TRD | 0 |  |  |  |  | 0 | 9000-1000- - | DISPATCH FOR ALL TRD | 0 |  |  |  |  | 0
Labor | L | 9000 | 9000-2000- - | RECEIVING | 0 | 0 | 0 | 0 | 9000-2000- - | RECEIVING | 0 |  |  |  |  | 0 | 9000-2000- - | RECEIVING | 0 |  |  |  |  | 0 | 9000-2000- - | RECEIVING | 0 |  |  |  |  | 0 | 9000-2000- - | RECEIVING | 0 |  |  |  |  | 0
Labor | L | 9000 | 9000-3000- - | MH - SHIPPING | 0 | 0 | 0 | 0 | 9000-3000- - | MH - SHIPPING | 0 |  |  |  |  | 0 | 9000-3000- - | MH - SHIPPING | 0 |  |  |  |  | 0 | 9000-3000- - | MH - SHIPPING | 0 |  |  |  |  | 0 | 9000-3000- - | MH - SHIPPING | 0 |  |  |  |  | 0
Labor | L | 9000 | 9000-5000- - | DELIVERY-ALL TRADES | 0 | 0 | 0 | 0 | 9000-5000- - | DELIVERY-ALL TRADES | 0 |  |  |  |  | 0 | 9000-5000- - | DELIVERY-ALL TRADES | 0 |  |  |  |  | 0 | 9000-5000- - | DELIVERY-ALL TRADES | 0 |  |  |  |  | 0 | 9000-5000- - | DELIVERY-ALL TRADES | 0 |  |  |  |  | 0
Labor | L | 9000 | 9000-6000- - | MATERIAL RETURNS | 0 | 0 | 0 | 0 | 9000-6000- - | MATERIAL RETURNS | 0 |  |  |  |  | 0 | 9000-6000- - | MATERIAL RETURNS | 0 |  |  |  |  | 0 | 9000-6000- - | MATERIAL RETURNS | 0 |  |  |  |  | 0 | 9000-6000- - | MATERIAL RETURNS | 0 |  |  |  |  | 0
Labor | L | 9000 | 9000-7000- - | TOOL ROOM-ORDR & RET | 0 | 0 | 0 | 0 | 9000-7000- - | TOOL ROOM-ORDR & RET | 0 |  |  |  |  | 0 | 9000-7000- - | TOOL ROOM-ORDR & RET | 0 |  |  |  |  | 0 | 9000-7000- - | TOOL ROOM-ORDR & RET | 0 |  |  |  |  | 0 | 9000-7000- - | TOOL ROOM-ORDR & RET | 0 |  |  |  |  | 0
Labor | L | 9200 | 9200-0000- - | MULTIPLE | 0 | 0 | 0 | 0 | 9200-0000- - | MULTIPLE | 0 | 0 |  |  | 0 | 0 | 9200-0000- - | MULTIPLE | 0 | 0 |  |  | 0 | 0 | 9200-0000- - | MULTIPLE | 0 | 0 |  |  | 0 | 0 | 9200-0000- - | MULTIPLE | 0 | 0 |  |  | 0 | 0
Labor | L | 9300 | 9300-0000- - | MULTIPLE | 0 | 0 | 0 | 0 | 9300-0000- - | MULTIPLE | 0 | 0 |  |  | 0 | 0 | 9300-0000- - | MULTIPLE | 0 | 0 |  |  | 0 | 0 | 9300-0000- - | MULTIPLE | 0 | 0 |  |  | 0 | 0 | 9300-0000- - | MULTIPLE | 0 | 0 |  |  | 0 | 0
Labor | L | 9500 | 9500-0000- - | CAD Backgrounds | 2192 | 2192 | 0 | 0 | 9500-0000- - | CAD Backgrounds | 2192 | 0 |  |  | 0 | 2192 | 9500-0000- - | CAD Backgrounds | 2192 | 0 |  |  | 0 | 2192 | 9500-0000- - | CAD Backgrounds | 0 | 0 |  |  | 0 | 0 | 9500-0000- - | CAD Backgrounds | 0 | 0 |  |  | 0 | 0
Labor | L | 9500 | 9500-0001- - | SHOP OFFICE COORD | 0 | 0 | 0 | 0 | 9500-0001- - | SHOP OFFICE COORD | 0 |  |  |  |  | 0 | 9500-0001- - | SHOP OFFICE COORD | 0 |  |  |  |  | 0 | 9500-0001- - | SHOP OFFICE COORD | 0 |  |  |  |  | 0 | 9500-0001- - | SHOP OFFICE COORD | 0 |  |  |  |  | 0
Labor | L | 9500 | 9500-0002- - | SUPERVISION | 78 | 78 | 0 | 0 | 9500-0002- - | SUPERVISION | 78 |  |  |  |  | 78 | 9500-0002- - | SUPERVISION | 78 |  |  |  |  | 78 | 9500-0002- - | SUPERVISION | 0 |  |  |  |  | 0 | 9500-0002- - | SUPERVISION | 0 |  |  |  |  | 0
Labor | L | 9500 | 9500-0003- - | MH - SHOP FAB & REC. | 684 | 684 | 0 | 0 | 9500-0003- - | MH - SHOP FAB & REC. | 684 |  |  |  |  | 684 | 9500-0003- - | MH - SHOP FAB & REC. | 684 |  |  |  |  | 684 | 9500-0003- - | MH - SHOP FAB & REC. | 0 |  |  |  |  | 0 | 9500-0003- - | MH - SHOP FAB & REC. | 0 |  |  |  |  | 0
Labor | L | 9500 | 9500-1195- - | CYBERMATION INPUT | 0 | 0 | 0 | 0 | 9500-1195- - | CYBERMATION INPUT | 0 |  |  |  |  | 0 | 9500-1195- - | CYBERMATION INPUT | 0 |  |  |  |  | 0 | 9500-1195- - | CYBERMATION INPUT | 0 |  |  |  |  | 0 | 9500-1195- - | CYBERMATION INPUT | 0 |  |  |  |  | 0
Labor | L | 9500 | 9500-1251- - | MULTIPLE | 0 | 0 | 0 | 0 | 9500-1251- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1251- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1251- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1251- - | MULTIPLE | 0 | 0 |  |  |  | 0
Labor | L | 9500 | 9500-1255- - | MULTIPLE | 0 | 0 | 0 | 0 | 9500-1255- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1255- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1255- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1255- - | MULTIPLE | 0 | 0 |  |  |  | 0
Labor | L | 9500 | 9500-1290- - | MULTIPLE | 0 | 0 | 0 | 0 | 9500-1290- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1290- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1290- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1290- - | MULTIPLE | 0 | 0 |  |  |  | 0
Labor | L | 9500 | 9500-1352- - | MULTIPLE | 0 | 0 | 0 | 0 | 9500-1352- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1352- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1352- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1352- - | MULTIPLE | 0 | 0 |  |  |  | 0
Labor | L | 9500 | 9500-1399- - | MULTIPLE | 0 | 0 | 0 | 0 | 9500-1399- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1399- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1399- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1399- - | MULTIPLE | 0 | 0 |  |  |  | 0
Labor | L | 9500 | 9500-1453- - | MULTIPLE | 0 | 0 | 0 | 0 | 9500-1453- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1453- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1453- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1453- - | MULTIPLE | 0 | 0 |  |  |  | 0
Labor | L | 9500 | 9500-1492- - | MULTIPLE | 0 | 0 | 0 | 0 | 9500-1492- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1492- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1492- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1492- - | MULTIPLE | 0 | 0 |  |  |  | 0
Labor | L | 9500 | 9500-1562- - | MULTIPLE | 0 | 0 | 0 | 0 | 9500-1562- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1562- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1562- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1562- - | MULTIPLE | 0 | 0 |  |  |  | 0
Labor | L | 9500 | 9500-1563- - | MULTIPLE | 0 | 0 | 0 | 0 | 9500-1563- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1563- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1563- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1563- - | MULTIPLE | 0 | 0 |  |  |  | 0
Labor | L | 9500 | 9500-1691- - | MULTIPLE | 0 | 0 | 0 | 0 | 9500-1691- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1691- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1691- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1691- - | MULTIPLE | 0 | 0 |  |  |  | 0
Labor | L | 9500 | 9500-1754- - | MULTIPLE | 0 | 0 | 0 | 0 | 9500-1754- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1754- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1754- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1754- - | MULTIPLE | 0 | 0 |  |  |  | 0
Labor | L | 9500 | 9500-1765- - | MULTIPLE | 0 | 0 | 0 | 0 | 9500-1765- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1765- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1765- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1765- - | MULTIPLE | 0 | 0 |  |  |  | 0
Labor | L | 9500 | 9500-1867- - | MULTIPLE | 0 | 0 | 0 | 0 | 9500-1867- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1867- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1867- - | MULTIPLE | 0 | 0 |  |  |  | 0 | 9500-1867- - | MULTIPLE | 0 | 0 |  |  |  | 0
Labor | L | 9600 | 9600-0000- - | ELECTRICAL SHOP* | 0 | 0 | 0 | 0 | 9600-0000- - | ELECTRICAL SHOP* | 0 | 0 |  |  | 0 | 0 | 9600-0000- - | ELECTRICAL SHOP* | 0 | 0 |  |  | 0 | 0 | 9600-0000- - | ELECTRICAL SHOP* | 0 | 0 |  |  | 0 | 0 | 9600-0000- - | ELECTRICAL SHOP* | 0 | 0 |  |  | 0 | 0
Labor | L | 9700 | 9700-0000- - | COMMUNICATIONS SHOP* | 0 | 0 | 0 | 0 | 9700-0000- - | COMMUNICATIONS SHOP* | 0 | 0 |  |  | 0 | 0 | 9700-0000- - | COMMUNICATIONS SHOP* | 0 | 0 |  |  | 0 | 0 | 9700-0000- - | COMMUNICATIONS SHOP* | 0 | 0 |  |  | 0 | 0 | 9700-0000- - | COMMUNICATIONS SHOP* | 0 | 0 |  |  | 0 | 0
Labor | L | 9999 | 9999-9048- - | STAFF BURDEN | 2604 | 2604 | 0 | 0 | 9999-9048- - | STAFF BURDEN | 2604 |  |  |  |  | 2604 | 9999-9048- - | STAFF BURDEN | 2604 |  |  |  |  | 2604 | 9999-9048- - | STAFF BURDEN | 0 |  |  |  |  | 0 | 9999-9048- - | STAFF BURDEN | 0 |  |  |  |  | 0
Labor | L | 9999 | 9999-9049- - | FIELD BURDEN | 3886 | 3886 | 0 | 0 | 9999-9049- - | FIELD BURDEN | 3886 |  |  |  |  | 3886 | 9999-9049- - | FIELD BURDEN | 3886 |  |  |  |  | 3886 | 9999-9049- - | FIELD BURDEN | 0 |  |  |  |  | 0 | 9999-9049- - | FIELD BURDEN | 0 |  |  |  |  | 0
Labor | L | 9999 | 9999-9050- - | SM SHOP BURDEN | 1034 | 1034 | 0 | 0 | 9999-9050- - | SM SHOP BURDEN | 1034 |  |  |  |  | 1034 | 9999-9050- - | SM SHOP BURDEN | 1034 |  |  |  |  | 1034 | 9999-9050- - | SM SHOP BURDEN | 0 |  |  |  |  | 0 | 9999-9050- - | SM SHOP BURDEN | 0 |  |  |  |  | 0
Labor | L | 9999 | 9999-9997- - | TRAVEL TIME | 0 | 0 | 0 | 0 | 9999-9997- - | TRAVEL TIME | 0 |  |  |  |  | 0 | 9999-9997- - | TRAVEL TIME | 0 |  |  |  |  | 0 | 9999-9997- - | TRAVEL TIME | 0 |  |  |  |  | 0 | 9999-9997- - | TRAVEL TIME | 0 |  |  |  |  | 0
Labor | L | 9999 | 9999-9998-000000- | MULTIPLE | 0 | 0 | 0 | 0 | 9999-9998-000000- | MULTIPLE | 0 | 0 |  | 0 | 0 | 0 | 9999-9998-000000- | MULTIPLE | 0 | 0 |  | 0 | 0 | 0 | 9999-9998-000000- | MULTIPLE | 0 | 0 |  | 0 | 0 | 0 | 9999-9998-000000- | MULTIPLE | 0 | 0 |  | 0 | 0 | 0
Labor | L | 9999 | 9999-9998-000204- | PLBG PRE-DETAILING | 0 | 0 | 0 | 0 | 9999-9998-000204- | PLBG PRE-DETAILING | 0 |  |  |  |  | 0 | 9999-9998-000204- | PLBG PRE-DETAILING | 0 |  |  |  |  | 0 | 9999-9998-000204- | PLBG PRE-DETAILING | 0 |  |  |  |  | 0 | 9999-9998-000204- | PLBG PRE-DETAILING | 0 |  |  |  |  | 0
Labor | L | 9999 | 9999-9998-000298- | WARRANTY | 0 | 0 | 0 | 0 | 9999-9998-000298- | WARRANTY | 0 |  |  |  |  | 0 | 9999-9998-000298- | WARRANTY | 0 |  |  |  |  | 0 | 9999-9998-000298- | WARRANTY | 0 |  |  |  |  | 0 | 9999-9998-000298- | WARRANTY | 0 |  |  |  |  | 0
Labor | L | 9999 | 9999-9998-000304- | DSGN ASSIST PRE-DET | 0 | 0 | 0 | 0 | 9999-9998-000304- | DSGN ASSIST PRE-DET | 0 |  |  |  |  | 0 | 9999-9998-000304- | DSGN ASSIST PRE-DET | 0 |  |  |  |  | 0 | 9999-9998-000304- | DSGN ASSIST PRE-DET | 0 |  |  |  |  | 0 | 9999-9998-000304- | DSGN ASSIST PRE-DET | 0 |  |  |  |  | 0
Labor | L | 9999 | 9999-9998-000698- | WARRANTY | 0 | 0 | 0 | 0 | 9999-9998-000698- | WARRANTY | 0 |  |  |  |  | 0 | 9999-9998-000698- | WARRANTY | 0 |  |  |  |  | 0 | 9999-9998-000698- | WARRANTY | 0 |  |  |  |  | 0 | 9999-9998-000698- | WARRANTY | 0 |  |  |  |  | 0
Labor | L | 9999 | 9999-9998-000798- | WARRANTY | 0 | 0 | 0 | 0 | 9999-9998-000798- | WARRANTY | 0 |  |  |  |  | 0 | 9999-9998-000798- | WARRANTY | 0 |  |  |  |  | 0 | 9999-9998-000798- | WARRANTY | 0 |  |  |  |  | 0 | 9999-9998-000798- | WARRANTY | 0 |  |  |  |  | 0
Labor | L | 9999 | 9999-9999- - | INTERNAL | 0 | 0 | 0 | 0 | 9999-9999- - | INTERNAL | 0 |  |  |  |  | 0 | 9999-9999- - | INTERNAL | 0 |  |  |  |  | 0 | 9999-9999- - | INTERNAL | 0 |  |  |  |  | 0 | 9999-9999- - | INTERNAL | 0 |  |  |  |  | 0
Material | M | 0131 | 0131-1150- - | General Construction | 5000 | 5000 | 0 | 0 | 2320-9000- - | MAJOR EQUIPMENT |  | 0 |  |  |  | 0 | 2320-9000- - | MAJOR EQUIPMENT |  | 0 |  |  |  | 0 | 2320-9000- - | MAJOR EQUIPMENT |  | 0 |  |  |  | 0 | 2320-9000- - | MAJOR EQUIPMENT |  | 0 |  |  |  | 0
Material | M | 2100 | 2100-0000- - | MULTIPLE | 0 | 0 | 0 | 0 | 7000-0195- - | SHEET METAL (SHOP) |  | 2300 |  |  |  | 2300 | 7000-0195- - | SHEET METAL (SHOP) |  | 2300 |  |  |  | 2300 | 7000-0195- - | SHEET METAL (SHOP) |  | 0 |  |  |  | 0 | 7000-0195- - | SHEET METAL (SHOP) |  | 0 |  |  |  | 0
Material | M | 2200 | 2200-0000- - | Plumbing | 12050 | 12050 | 0 | 0 | 0100-0230- - | MCK OWNED EQ BURDEN |  |  | 1352 |  |  | 1352 | 0100-0230- - | MCK OWNED EQ BURDEN |  |  | 1352 |  |  | 1352 | 0100-0230- - | MCK OWNED EQ BURDEN |  |  | 0 |  |  | 0 | 0100-0230- - | MCK OWNED EQ BURDEN |  |  | 0 |  |  | 0
Material | M | 2300 | 2300-0000- - | HEATING, VENTILATING, AND AIR CONDITIONING (HVAC)* | 0 | 0 | 0 | 0 | 0100-0240- - | EQUIP BURDEN |  |  | 2116 |  |  | 2116 | 0100-0240- - | EQUIP BURDEN |  |  | 2116 |  |  | 2116 | 0100-0240- - | EQUIP BURDEN |  |  | 0 |  |  | 0 | 0100-0240- - | EQUIP BURDEN |  |  | 0 |  |  | 0
Material | M | 2320 | 2320-0000- - | MULTIPLE | 0 | 0 | 0 | 0 | 0100-0100- - | TRAVEL/PARKING UNION |  |  |  | 0 |  | 0 | 0100-0100- - | TRAVEL/PARKING UNION |  |  |  | 0 |  | 0 | 0100-0100- - | TRAVEL/PARKING UNION |  |  |  | 0 |  | 0 | 0100-0100- - | TRAVEL/PARKING UNION |  |  |  | 0 |  | 0
Material | M | 2320 | 2320-9000- - | MAJOR EQUIPMENT | 0 | 0 | 0 | 0 | 0100-0110- - | Parking* |  |  |  | 0 |  | 0 | 0100-0110- - | Parking* |  |  |  | 0 |  | 0 | 0100-0110- - | Parking* |  |  |  | 0 |  | 0 | 0100-0110- - | Parking* |  |  |  | 0 |  | 0
Material | M | 2330 | 2330-0000- - | Sheet Metal (field) | 300 | 300 | 0 | 0 | 0100-0120- - | Mileage |  |  |  | 0 |  | 0 | 0100-0120- - | Mileage |  |  |  | 0 |  | 0 | 0100-0120- - | Mileage |  |  |  | 0 |  | 0 | 0100-0120- - | Mileage |  |  |  | 0 |  | 0
Material | M | 2600 | 2600-0000- - | Electrical Material | 968 | 968 | 0 | 0 | 0100-0140- - | Per Diem* |  |  |  | 0 |  | 0 | 0100-0140- - | Per Diem* |  |  |  | 0 |  | 0 | 0100-0140- - | Per Diem* |  |  |  | 0 |  | 0 | 0100-0140- - | Per Diem* |  |  |  | 0 |  | 0
Material | M | 2700 | 2700-0000- - | COMMUNICATION SYSTEMS* | 0 | 0 | 0 | 0 | 0100-0210- - | RETURNABLE TOOLS |  |  |  | 1350 |  | 1350 | 0100-0210- - | RETURNABLE TOOLS |  |  |  | 1350 |  | 1350 | 0100-0210- - | RETURNABLE TOOLS |  |  |  | 0 |  | 0 | 0100-0210- - | RETURNABLE TOOLS |  |  |  | 0 |  | 0
Material | M | 7000 | 7000-0195- - | SHEET METAL (SHOP) | 2300 | 2300 | 0 | 0 | 0100-0220- - | CONSUMABLES |  |  |  | 0 |  | 0 | 0100-0220- - | CONSUMABLES |  |  |  | 0 |  | 0 | 0100-0220- - | CONSUMABLES |  |  |  | 0 |  | 0 | 0100-0220- - | CONSUMABLES |  |  |  | 0 |  | 0
Material | M | 9000 | 9000-0000- - | LOGISTICS - NONUNION | 0 | 0 | 0 | 0 | 0100-0500- - | 3RD PARTY RENTALS |  |  |  | 0 |  | 0 | 0100-0500- - | 3RD PARTY RENTALS |  |  |  | 0 |  | 0 | 0100-0500- - | 3RD PARTY RENTALS |  |  |  | 0 |  | 0 | 0100-0500- - | 3RD PARTY RENTALS |  |  |  | 0 |  | 0
Material | M | 9200 | 9200-0000- - | MULTIPLE | 0 | 0 | 0 | 0 | 0100-0680- - | DELIVERIES ALL TRDS |  |  |  | 0 |  | 0 | 0100-0680- - | DELIVERIES ALL TRDS |  |  |  | 0 |  | 0 | 0100-0680- - | DELIVERIES ALL TRDS |  |  |  | 0 |  | 0 | 0100-0680- - | DELIVERIES ALL TRDS |  |  |  | 0 |  | 0
Material | M | 9300 | 9300-0000- - | MULTIPLE | 0 | 0 | 0 | 0 | 0100-0870- - | Liability Insurance* |  |  |  | 0 |  | 0 | 0100-0870- - | Liability Insurance* |  |  |  | 0 |  | 0 | 0100-0870- - | Liability Insurance* |  |  |  | 0 |  | 0 | 0100-0870- - | Liability Insurance* |  |  |  | 0 |  | 0
Material | M | 9500 | 9500-0000- - | CAD Backgrounds | 0 | 0 | 0 | 0 | 0100-0880- - | Taxes* |  |  |  | 0 |  | 0 | 0100-0880- - | Taxes* |  |  |  | 0 |  | 0 | 0100-0880- - | Taxes* |  |  |  | 0 |  | 0 | 0100-0880- - | Taxes* |  |  |  | 0 |  | 0
Material | M | 9500 | 9500-1251- - | MULTIPLE | 0 | 0 | 0 | 0 | 0131-1705- - | TESTING |  |  |  |  | 0 | 0 | 0131-1705- - | TESTING |  |  |  |  | 0 | 0 | 0131-1705- - | TESTING |  |  |  |  | 0 | 0 | 0131-1705- - | TESTING |  |  |  |  | 0 | 0
Material | M | 9500 | 9500-1255- - | MULTIPLE | 0 | 0 | 0 | 0 | 0199-1000- - | POTENTIAL MARGIN |  |  |  |  | 0 | 0 | 0199-1000- - | POTENTIAL MARGIN |  |  |  |  | 0 | 0 | 0199-1000- - | POTENTIAL MARGIN |  |  |  |  | 0 | 0 | 0199-1000- - | POTENTIAL MARGIN |  |  |  |  | 0 | 0
Material | M | 9500 | 9500-1290- - | MULTIPLE | 0 | 0 | 0 | 0 | 0641-1000- - | CASEWORK |  |  |  |  | 35666 | 35666 | 0641-1000- - | CASEWORK |  |  |  |  | 35666 | 35666 | 0641-1000- - | CASEWORK |  |  |  |  | 0 | 0 | 0641-1000- - | CASEWORK |  |  |  |  | 0 | 0
Material | M | 9500 | 9500-1352- - | MULTIPLE | 0 | 0 | 0 | 0 | 0721-1000- - | INSULATION |  |  |  |  | 3500 | 3500 | 0721-1000- - | INSULATION |  |  |  |  | 3500 | 3500 | 0721-1000- - | INSULATION |  |  |  |  | 0 | 0 | 0721-1000- - | INSULATION |  |  |  |  | 0 | 0
Material | M | 9500 | 9500-1399- - | MULTIPLE | 0 | 0 | 0 | 0 | 1000-1000- - | SPECIALTIES |  |  |  |  | 0 | 0 | 1000-1000- - | SPECIALTIES |  |  |  |  | 0 | 0 | 1000-1000- - | SPECIALTIES |  |  |  |  | 0 | 0 | 1000-1000- - | SPECIALTIES |  |  |  |  | 0 | 0
Material | M | 9500 | 9500-1453- - | MULTIPLE | 0 | 0 | 0 | 0 | Grand Total |  | 44028 | 20618 | 3468 | 3868 | 39166 | 111148 | Grand Total |  | 44028 | 20618 | 3468 | 3868 | 39166 | 111148 | Grand Total |  | 0 | 0 | 0 | 0 | 0 | 0 | Grand Total |  | 0 | 0 | 0 | 0 | 0 | 0
Material | M | 9500 | 9500-1492- - | MULTIPLE | 0 | 0 | 0 | 0
Material | M | 9500 | 9500-1562- - | MULTIPLE | 0 | 0 | 0 | 0
Material | M | 9500 | 9500-1563- - | MULTIPLE | 0 | 0 | 0 | 0
Material | M | 9500 | 9500-1691- - | MULTIPLE | 0 | 0 | 0 | 0
Material | M | 9500 | 9500-1754- - | MULTIPLE | 0 | 0 | 0 | 0
Material | M | 9500 | 9500-1765- - | MULTIPLE | 0 | 0 | 0 | 0
Material | M | 9500 | 9500-1867- - | MULTIPLE | 0 | 0 | 0 | 0
Material | M | 9600 | 9600-0000- - | ELECTRICAL SHOP* | 0 | 0 | 0 | 0
Material | M | 9700 | 9700-0000- - | COMMUNICATIONS SHOP* | 0 | 0 | 0 | 0
Material | M | 9999 | 9999-9998-000000- | MULTIPLE | 0 | 0 | 0 | 0
McK Owned Equipment | E | 0100 | 0100-0230- - | MCK OWNED EQ BURDEN | 1352 | 1352 | 0 | 0
McK Owned Equipment | E | 0100 | 0100-0240- - | EQUIP BURDEN | 2116 | 2116 | 0 | 0
Other | O | 0100 | 0100-0000- - | GENERAL REQUIREMENTS* | 0 | 0 | 0 | 0
Other | O | 0100 | 0100-0100- - | TRAVEL/PARKING UNION | 0 | 0 | 0 | 0
Other | O | 0100 | 0100-0110- - | Parking* | 0 | 0 | 0 | 0
Other | O | 0100 | 0100-0120- - | Mileage | 0 | 0 | 0 | 0
Other | O | 0100 | 0100-0140- - | Per Diem* | 0 | 0 | 0 | 0
Other | O | 0100 | 0100-0191- - | Travel Time* - Carpenters & Drywall | 0 | 0 | 0 | 0
Other | O | 0100 | 0100-0192- - | Travel Time* - Electrical | 0 | 0 | 0 | 0
Other | O | 0100 | 0100-0193- - | Travel Time* - Laborers | 0 | 0 | 0 | 0
Other | O | 0100 | 0100-0194- - | Travel Time* - Painters | 0 | 0 | 0 | 0
Other | O | 0100 | 0100-0195- - | Travel Time* - Plumbing | 0 | 0 | 0 | 0
Other | O | 0100 | 0100-0196- - | Travel Time* - Sheet Metal | 0 | 0 | 0 | 0
Other | O | 0100 | 0100-0197- - | Travel Time* - Sprinklers | 0 | 0 | 0 | 0
Other | O | 0100 | 0100-0210- - | RETURNABLE TOOLS | 1350 | 1350 | 0 | 0
Other | O | 0100 | 0100-0220- - | CONSUMABLES | 0 | 0 | 0 | 0
Other | O | 0100 | 0100-0500- - | 3RD PARTY RENTALS | 0 | 0 | 0 | 0
Other | O | 0100 | 0100-0680- - | DELIVERIES ALL TRDS | 0 | 0 | 0 | 0
Other | O | 0100 | 0100-0800- - | OTHER DIRECT COSTS | 2518 | 2518 | 0 | 0
Other | O | 0100 | 0100-0870- - | Liability Insurance* | 0 | 0 | 0 | 0
Other | O | 0100 | 0100-0880- - | Taxes* | 0 | 0 | 0 | 0
Other | O | 2600 | 2600-0000- - | Electrical Material | 0 | 0 | 0 | 0
Other | O | 2700 | 2700-0000- - | COMMUNICATION SYSTEMS* | 0 | 0 | 0 | 0
Other | O | 9999 | 9999-9998-000000- | MULTIPLE | 0 | 0 | 0 | 0
Subcontract | S | 0100 | 0100-0000- - | GENERAL REQUIREMENTS* | 0 | 0 | 0 | 0
Subcontract | S | 0100 | 0100-0800- - | OTHER DIRECT COSTS | 0 | 0 | 0 | 0
Subcontract | S | 0131 | 0131-1705- - | TESTING | 0 | 0 | 0 | 0
Subcontract | S | 0131 | 0131-1900- - | MULTIPLE | 0 | 0 | 0 | 0
Subcontract | S | 0199 | 0199-1000- - | POTENTIAL MARGIN | 0 | 0 | 0 | 0
Subcontract | S | 0641 | 0641-1000- - | CASEWORK | 35666 | 35666 | 0 | 0
Subcontract | S | 0721 | 0721-1000- - | INSULATION | 3500 | 3500 | 0 | 0
Subcontract | S | 1000 | 1000-1000- - | SPECIALTIES | 0 | 0 | 0 | 0
Subcontract | S | 2100 | 2100-0000- - | MULTIPLE | 0 | 0 | 0 | 0
Subcontract | S | 2200 | 2200-0000- - | Plumbing | 0 | 0 | 0 | 0
Subcontract | S | 2300 | 2300-0000- - | HEATING, VENTILATING, AND AIR CONDITIONING (HVAC)* | 0 | 0 | 0 | 0
Subcontract | S | 2320 | 2320-0000- - | MULTIPLE | 0 | 0 | 0 | 0
Subcontract | S | 2330 | 2330-0000- - | Sheet Metal (field) | 0 | 0 | 0 | 0
Subcontract | S | 2600 | 2600-0000- - | Electrical Material | 0 | 0 | 0 | 0
Subcontract | S | 2700 | 2700-0000- - | COMMUNICATION SYSTEMS* | 0 | 0 | 0 | 0
Subcontract | S | 9200 | 9200-0000- - | MULTIPLE | 0 | 0 | 0 | 0
Subcontract | S | 9300 | 9300-0000- - | MULTIPLE | 0 | 0 | 0 | 0
Subcontract | S | 9500 | 9500-0000- - | CAD Backgrounds | 0 | 0 | 0 | 0
Subcontract | S | 9600 | 9600-0000- - | ELECTRICAL SHOP* | 0 | 0 | 0 | 0
Subcontract | S | 9700 | 9700-0000- - | COMMUNICATIONS SHOP* | 0 | 0 | 0 | 0
Subcontract | S | 9999 | 9999-9998-000000- | MULTIPLE | 0 | 0 | 0 | 0
Total |  |  |  |  | 111148 | 111148 | 0 | 0

## Job 10664-002
Contract | 10664-
Job Number | 10664-002 |  |  |  | Original | Current | Forecast | Projection
Job Description | Warranty for UW 4th Floor Lab Remodel |  |  | Labor | 1000 | 1100 | 1200 | 1050
Project Manager | ERIK PIECZATKOWSKI |  |  | Material | 0 | 0 | 0 | 0
Department | 02400 |  |  | Equipment | 0 | 0 | 0 | 0
GLDepartment | 0240 |  |  | SubContract | 0 | 0 | 0 | 0
Status | 1-Open |  |  | ODC | 0 | 0 | 0 | 0
Start | 2014-10-01 |  |  | Total | 1000 | 1100 | 1200 | 1050
End | 2015-10-01
[9 empty] | Sum of Original |  | Abbreviation | [5 empty] | Sum of Curr |  | Abbreviation | [5 empty] | Sum of Forecast |  | Abbreviation | [5 empty] | Sum of Projected |  | Abbreviation
Description | Abbreviation | PhasePrefix | Phase | PhaseDesc | Original | Curr | Forecast | Projected | Phase | PhaseDesc | L | M | E | O | S | Grand Total | Phase | PhaseDesc | L | M | E | O | S | Grand Total | Phase | PhaseDesc | L | M | E | O | S | Grand Total | Phase | PhaseDesc | L | M | E | O | S | Grand Total
Material | M | 0 | 0000-0000- - | None | 0 | 0 | 0 | 0 | 0100-0000- - | GENERAL REQUIREMENTS* | 1000 |  |  | 0 |  | 1000 | 0100-0000- - | GENERAL REQUIREMENTS* | 1100 |  |  | 0 |  | 1100 | 0100-0000- - | GENERAL REQUIREMENTS* | 1200 |  |  | 0 |  | 1200 | 0100-0000- - | GENERAL REQUIREMENTS* | 1050 |  |  | 0 |  | 1050
Subcontract | S | 0 | 0000-0000- - | None | 0 | 0 | 0 | 0 | 0100-0191- - | Travel Time* - Carpenters & Drywall | 0 |  |  |  |  | 0 | 0100-0191- - | Travel Time* - Carpenters & Drywall | 0 |  |  |  |  | 0 | 0100-0191- - | Travel Time* - Carpenters & Drywall | 0 |  |  |  |  | 0 | 0100-0191- - | Travel Time* - Carpenters & Drywall | 0 |  |  |  |  | 0
Labor | L | 100 | 0100-0000- - | GENERAL REQUIREMENTS* | 1000 | 1100 | 1200 | 1050 | 0100-0192- - | Travel Time* - Electrical | 0 |  |  |  |  | 0 | 0100-0192- - | Travel Time* - Electrical | 0 |  |  |  |  | 0 | 0100-0192- - | Travel Time* - Electrical | 0 |  |  |  |  | 0 | 0100-0192- - | Travel Time* - Electrical | 0 |  |  |  |  | 0
Labor | L | 100 | 0100-0191- - | Travel Time* - Carpenters & Drywall | 0 | 0 | 0 | 0 | 0100-0193- - | Travel Time* - Laborers | 0 |  |  |  |  | 0 | 0100-0193- - | Travel Time* - Laborers | 0 |  |  |  |  | 0 | 0100-0193- - | Travel Time* - Laborers | 0 |  |  |  |  | 0 | 0100-0193- - | Travel Time* - Laborers | 0 |  |  |  |  | 0
Labor | L | 100 | 0100-0192- - | Travel Time* - Electrical | 0 | 0 | 0 | 0 | 0100-0194- - | Travel Time* - Painters | 0 |  |  |  |  | 0 | 0100-0194- - | Travel Time* - Painters | 0 |  |  |  |  | 0 | 0100-0194- - | Travel Time* - Painters | 0 |  |  |  |  | 0 | 0100-0194- - | Travel Time* - Painters | 0 |  |  |  |  | 0
Labor | L | 100 | 0100-0193- - | Travel Time* - Laborers | 0 | 0 | 0 | 0 | 0100-0195- - | Travel Time* - Plumbing | 0 |  |  |  |  | 0 | 0100-0195- - | Travel Time* - Plumbing | 0 |  |  |  |  | 0 | 0100-0195- - | Travel Time* - Plumbing | 0 |  |  |  |  | 0 | 0100-0195- - | Travel Time* - Plumbing | 0 |  |  |  |  | 0
Labor | L | 100 | 0100-0194- - | Travel Time* - Painters | 0 | 0 | 0 | 0 | 0100-0196- - | Travel Time* - Sheet Metal | 0 |  |  |  |  | 0 | 0100-0196- - | Travel Time* - Sheet Metal | 0 |  |  |  |  | 0 | 0100-0196- - | Travel Time* - Sheet Metal | 0 |  |  |  |  | 0 | 0100-0196- - | Travel Time* - Sheet Metal | 0 |  |  |  |  | 0
Labor | L | 100 | 0100-0195- - | Travel Time* - Plumbing | 0 | 0 | 0 | 0 | 0100-0197- - | Travel Time* - Sprinklers | 0 |  |  |  |  | 0 | 0100-0197- - | Travel Time* - Sprinklers | 0 |  |  |  |  | 0 | 0100-0197- - | Travel Time* - Sprinklers | 0 |  |  |  |  | 0 | 0100-0197- - | Travel Time* - Sprinklers | 0 |  |  |  |  | 0
Labor | L | 100 | 0100-0196- - | Travel Time* - Sheet Metal | 0 | 0 | 0 | 0 | 0100-0800- - | MISCELLANEOUS EXPENSES* |  |  |  | 0 |  | 0 | 0100-0800- - | MISCELLANEOUS EXPENSES* |  |  |  | 0 |  | 0 | 0100-0800- - | MISCELLANEOUS EXPENSES* |  |  |  | 0 |  | 0 | 0100-0800- - | MISCELLANEOUS EXPENSES* |  |  |  | 0 |  | 0
Labor | L | 100 | 0100-0197- - | Travel Time* - Sprinklers | 0 | 0 | 0 | 0 | 2100-0000- - | FIRE SUPPRESSION* | 0 |  |  |  |  | 0 | 2100-0000- - | FIRE SUPPRESSION* | 0 |  |  |  |  | 0 | 2100-0000- - | FIRE SUPPRESSION* | 0 |  |  |  |  | 0 | 2100-0000- - | FIRE SUPPRESSION* | 0 |  |  |  |  | 0
Labor | L | 600 | 0600-1000- - | WOOD, PLASTICS & COMPOSITES* (Carpenters) | 0 | 0 | 0 | 0 | 2200-0000- - | PLUMBING FIELD* | 0 |  |  |  |  | 0 | 2200-0000- - | PLUMBING FIELD* | 0 |  |  |  |  | 0 | 2200-0000- - | PLUMBING FIELD* | 0 |  |  |  |  | 0 | 2200-0000- - | PLUMBING FIELD* | 0 |  |  |  |  | 0
Labor | L | 2100 | 2100-0000- - | FIRE SUPPRESSION* | 0 | 0 | 0 | 0 | 2300-0000- - | HEATING, VENTILATING, AND AIR CONDITIONING (HVAC)* | 0 |  |  |  |  | 0 | 2300-0000- - | HEATING, VENTILATING, AND AIR CONDITIONING (HVAC)* | 0 |  |  |  |  | 0 | 2300-0000- - | HEATING, VENTILATING, AND AIR CONDITIONING (HVAC)* | 0 |  |  |  |  | 0 | 2300-0000- - | HEATING, VENTILATING, AND AIR CONDITIONING (HVAC)* | 0 |  |  |  |  | 0
Labor | L | 2200 | 2200-0000- - | PLUMBING FIELD* | 0 | 0 | 0 | 0 | 2320-0000- - | PIPING FIELD* | 0 |  |  |  |  | 0 | 2320-0000- - | PIPING FIELD* | 0 |  |  |  |  | 0 | 2320-0000- - | PIPING FIELD* | 0 |  |  |  |  | 0 | 2320-0000- - | PIPING FIELD* | 0 |  |  |  |  | 0
Labor | L | 2300 | 2300-0000- - | HEATING, VENTILATING, AND AIR CONDITIONING (HVAC)* | 0 | 0 | 0 | 0 | 2330-0000- - | SHEET METAL FIELD* | 0 |  |  |  |  | 0 | 2330-0000- - | SHEET METAL FIELD* | 0 |  |  |  |  | 0 | 2330-0000- - | SHEET METAL FIELD* | 0 |  |  |  |  | 0 | 2330-0000- - | SHEET METAL FIELD* | 0 |  |  |  |  | 0
Labor | L | 2320 | 2320-0000- - | PIPING FIELD* | 0 | 0 | 0 | 0 | 2600-0000- - | ELECTRICAL* | 0 |  |  |  |  | 0 | 2600-0000- - | ELECTRICAL* | 0 |  |  |  |  | 0 | 2600-0000- - | ELECTRICAL* | 0 |  |  |  |  | 0 | 2600-0000- - | ELECTRICAL* | 0 |  |  |  |  | 0
Labor | L | 2330 | 2330-0000- - | SHEET METAL FIELD* | 0 | 0 | 0 | 0 | 2700-0000- - | COMMUNICATION SYSTEMS* | 0 |  |  |  |  | 0 | 2700-0000- - | COMMUNICATION SYSTEMS* | 0 |  |  |  |  | 0 | 2700-0000- - | COMMUNICATION SYSTEMS* | 0 |  |  |  |  | 0 | 2700-0000- - | COMMUNICATION SYSTEMS* | 0 |  |  |  |  | 0
Labor | L | 2600 | 2600-0000- - | ELECTRICAL* | 0 | 0 | 0 | 0 | 9000-0000- - | SHOP LOGISTICS* | 0 |  |  |  |  | 0 | 9000-0000- - | SHOP LOGISTICS* | 0 |  |  |  |  | 0 | 9000-0000- - | SHOP LOGISTICS* | 0 |  |  |  |  | 0 | 9000-0000- - | SHOP LOGISTICS* | 0 |  |  |  |  | 0
Labor | L | 2700 | 2700-0000- - | COMMUNICATION SYSTEMS* | 0 | 0 | 0 | 0 | 9200-0000- - | PLUMBING SHOP* | 0 |  |  |  |  | 0 | 9200-0000- - | PLUMBING SHOP* | 0 |  |  |  |  | 0 | 9200-0000- - | PLUMBING SHOP* | 0 |  |  |  |  | 0 | 9200-0000- - | PLUMBING SHOP* | 0 |  |  |  |  | 0
Labor | L | 9000 | 9000-0000- - | SHOP LOGISTICS* | 0 | 0 | 0 | 0 | 9300-0000- - | PIPING SHOP* | 0 |  |  |  |  | 0 | 9300-0000- - | PIPING SHOP* | 0 |  |  |  |  | 0 | 9300-0000- - | PIPING SHOP* | 0 |  |  |  |  | 0 | 9300-0000- - | PIPING SHOP* | 0 |  |  |  |  | 0
Labor | L | 9200 | 9200-0000- - | PLUMBING SHOP* | 0 | 0 | 0 | 0 | 9500-0000- - | SHEET METAL SHOP* | 0 |  |  |  |  | 0 | 9500-0000- - | SHEET METAL SHOP* | 0 |  |  |  |  | 0 | 9500-0000- - | SHEET METAL SHOP* | 0 |  |  |  |  | 0 | 9500-0000- - | SHEET METAL SHOP* | 0 |  |  |  |  | 0
Labor | L | 9300 | 9300-0000- - | PIPING SHOP* | 0 | 0 | 0 | 0 | 9600-0000- - | ELECTRICAL SHOP* | 0 |  |  |  |  | 0 | 9600-0000- - | ELECTRICAL SHOP* | 0 |  |  |  |  | 0 | 9600-0000- - | ELECTRICAL SHOP* | 0 |  |  |  |  | 0 | 9600-0000- - | ELECTRICAL SHOP* | 0 |  |  |  |  | 0
Labor | L | 9500 | 9500-0000- - | SHEET METAL SHOP* | 0 | 0 | 0 | 0 | 9700-0000- - | COMMUNICATIONS SHOP* | 0 |  |  |  |  | 0 | 9700-0000- - | COMMUNICATIONS SHOP* | 0 |  |  |  |  | 0 | 9700-0000- - | COMMUNICATIONS SHOP* | 0 |  |  |  |  | 0 | 9700-0000- - | COMMUNICATIONS SHOP* | 0 |  |  |  |  | 0
Labor | L | 9600 | 9600-0000- - | ELECTRICAL SHOP* | 0 | 0 | 0 | 0 | 0100-0240- - | McKinstry Truck Charge* |  |  | 0 |  |  | 0 | 0100-0240- - | McKinstry Truck Charge* |  |  | 0 |  |  | 0 | 0100-0240- - | McKinstry Truck Charge* |  |  | 0 |  |  | 0 | 0100-0240- - | McKinstry Truck Charge* |  |  | 0 |  |  | 0
Labor | L | 9700 | 9700-0000- - | COMMUNICATIONS SHOP* | 0 | 0 | 0 | 0 | 0100-0100- - | TRAVEL EXPENSES* |  |  |  | 0 |  | 0 | 0100-0100- - | TRAVEL EXPENSES* |  |  |  | 0 |  | 0 | 0100-0100- - | TRAVEL EXPENSES* |  |  |  | 0 |  | 0 | 0100-0100- - | TRAVEL EXPENSES* |  |  |  | 0 |  | 0
McK Owned Equipment | E | 100 | 0100-0240- - | McKinstry Truck Charge* | 0 | 0 | 0 | 0 | 0100-0110- - | Parking* |  |  |  | 0 |  | 0 | 0100-0110- - | Parking* |  |  |  | 0 |  | 0 | 0100-0110- - | Parking* |  |  |  | 0 |  | 0 | 0100-0110- - | Parking* |  |  |  | 0 |  | 0
Other | O | 100 | 0100-0000- - | GENERAL REQUIREMENTS* | 0 | 0 | 0 | 0 | 0100-0140- - | Per Diem* |  |  |  | 0 |  | 0 | 0100-0140- - | Per Diem* |  |  |  | 0 |  | 0 | 0100-0140- - | Per Diem* |  |  |  | 0 |  | 0 | 0100-0140- - | Per Diem* |  |  |  | 0 |  | 0
Other | O | 100 | 0100-0100- - | TRAVEL EXPENSES* | 0 | 0 | 0 | 0 | 0100-0870- - | Liability Insurance* |  |  |  | 0 |  | 0 | 0100-0870- - | Liability Insurance* |  |  |  | 0 |  | 0 | 0100-0870- - | Liability Insurance* |  |  |  | 0 |  | 0 | 0100-0870- - | Liability Insurance* |  |  |  | 0 |  | 0
Other | O | 100 | 0100-0110- - | Parking* | 0 | 0 | 0 | 0 | 0100-0880- - | Taxes* |  |  |  | 0 |  | 0 | 0100-0880- - | Taxes* |  |  |  | 0 |  | 0 | 0100-0880- - | Taxes* |  |  |  | 0 |  | 0 | 0100-0880- - | Taxes* |  |  |  | 0 |  | 0
Other | O | 100 | 0100-0120- - | Mileage* | 0 | 0 | 0 | 0 | 0600-1000- - | WOOD, PLASTICS & COMPOSITES* (Carpenters) | 0 |  |  |  |  | 0 | 0600-1000- - | WOOD, PLASTICS & COMPOSITES* (Carpenters) | 0 |  |  |  |  | 0 | 0600-1000- - | WOOD, PLASTICS & COMPOSITES* (Carpenters) | 0 |  |  |  |  | 0 | 0600-1000- - | WOOD, PLASTICS & COMPOSITES* (Carpenters) | 0 |  |  |  |  | 0
Other | O | 100 | 0100-0140- - | Per Diem* | 0 | 0 | 0 | 0 | 0100-0120- - | Mileage* |  |  |  | 0 |  | 0 | 0100-0120- - | Mileage* |  |  |  | 0 |  | 0 | 0100-0120- - | Mileage* |  |  |  | 0 |  | 0 | 0100-0120- - | Mileage* |  |  |  | 0 |  | 0
Other | O | 100 | 0100-0500- - | RENTALS* | 0 | 0 | 0 | 0 | 0100-0500- - | RENTALS* |  |  |  | 0 |  | 0 | 0100-0500- - | RENTALS* |  |  |  | 0 |  | 0 | 0100-0500- - | RENTALS* |  |  |  | 0 |  | 0 | 0100-0500- - | RENTALS* |  |  |  | 0 |  | 0
Other | O | 100 | 0100-0800- - | MISCELLANEOUS EXPENSES* | 0 | 0 | 0 | 0 | 0000-0000- - | None |  | 0 |  |  | 0 | 0 | 0000-0000- - | None |  | 0 |  |  | 0 | 0 | 0000-0000- - | None |  | 0 |  |  | 0 | 0 | 0000-0000- - | None |  | 0 |  |  | 0 | 0
Other | O | 100 | 0100-0870- - | Liability Insurance* | 0 | 0 | 0 | 0 | Grand Total |  | 1000 | 0 | 0 | 0 | 0 | 1000 | Grand Total |  | 1100 | 0 | 0 | 0 | 0 | 1100 | Grand Total |  | 1200 | 0 | 0 | 0 | 0 | 1200 | Grand Total |  | 1050 | 0 | 0 | 0 | 0 | 1050
Other | O | 100 | 0100-0880- - | Taxes* | 0 | 0 | 0 | 0
Total |  |  |  |  | 1000 | 1100 | 1200 | 1050